## Sheet1
Feature | Estimate (storypoints) | Completed (storypoints) | Actual cost (1000s of dollars)
Home Screen | 4 | 4 | 5
Settings Screen | 6 | 6 | 10
Game Screen | 7 | 7 | 15
Leaderboard Screen | 6 | 6 | 10
Win/Lose Button | 3 | 3 | 5
Play game against AI | 16
Play game against other people | 12
iOS device compatibility | 3
Totals | 57 | 26 | 45
Total budget = | 90000
Planned sprints = | 3
Total story points = | 57
Sprint #2 completed
Story points completed = | 26
Planned value = | 66% of $90,000 = $60,000
Actual percent completed = | 45.61%
Earned value = | 41052.6316